## Sheet1
RISK REGISTER
Project Name: Virtual Event Execution and Management
Project Manager(s): Sadiya Siddika Afrin, Shadrack Nyarango
ID | Date Raised | Risk Description | Likelihood | Impact | Severity | Proximity | Owner | Mitigating Action | Contingent Action | Progress on Actions | Status
R001 | 2025-10-03 | Platform crashes, connectivity issues, or software bugs disrupting the event. | High | High | High | Event Day | Technical Support Team | Conduct multiple dry runs, have a backup platform ready, and ensure technical support is available. | Switch to backup platform, provide real-time troubleshooting. | Dry runs scheduled, backup identified. | Open
R002 | 2025-10-03 | Failure to attract enough attendees due to poor marketing or scheduling conflicts. | High | High | High | Pre-Event | Marketing Team | Implement aggressive marketing, use social media ads, and offer incentives (e.g., early-bird perks). | Extend marketing efforts, offer last-minute promotions. | Marketing campaign launched. | Open
R003 | 2025-11-03 | Key speakers cancel last minute, affecting the agenda and session quality. | Medium | High | High | Event Day | Event Coordinator | Have backup speakers or pre-recorded content ready. Ensure clear speaker contracts. | Adjust schedule, use additional moderators. | Backup speakers identified. | Open
R004 | 2025-12-03 | Attendees lose interest, leading to lower participation and interaction. | Medium | Medium | Medium | Event Day | Session Moderator | Use live polls, Q&A sessions, and interactive activities. Keep sessions concise and engaging. | Re-engage through direct interaction, shorter sessions. | Engagement activities planned. | Open
R005 | 2025-12-03 | Loss of attendee data or session recordings due to system failures. | Low | Medium | Medium | During & Post-Event | Data & Feedback Analyst | Regularly back up all data and use cloud storage. Ensure compliance with data security best practices. | Restore from backups, notify attendees. | Backup solutions implemented. | Open
R006 | 2025-12-03 | A sudden influx of attendees overwhelms the platform, leading to lag or access issues. | Low | Medium | Medium | Event Day | Event Coordinator | Cap registrations based on platform capacity and monitor sign-ups closely. | Increase server capacity, adjust entry rules. | Capacity limits set. | Open
R007 | 13/03/2025 | Attendees from different regions may struggle to join due to inconvenient timing. | Medium | Medium | Medium | Pre-Event | Event Coordinator | Offer multiple sessions or record and provide on-demand access. Communicate timing well in advance. | Provide post-event access. | Schedule adjusted. | Open
R008 | 13/03/2025 | Unauthorized access, hacking attempts, or phishing attacks targeting the event platform. | Low | High | High | Pre & During Event | Technical Support Team | Use secure logins, enable multi-factor authentication (MFA), and monitor for suspicious activities. | Activate emergency security measures, notify affected users. | Security protocols in place. | Open
R009 | 14/03/2025 | Lack of coordination between marketing, technical, and event management teams leading to errors. | Medium | Medium | Medium | Throughout Project | Project Manager | Hold regular team meetings, use project management tools (Trello, Slack), and document responsibilities clearly. | Assign additional coordinators, escalate issues quickly. | Coordination meetings scheduled. | Open
R010 | 14/03/2025 | Uncontrolled expansion of event features, leading to resource strain and delays. | Medium | High | High | Throughout Project | Project Manager | Clearly define event scope, get stakeholder approval early, and enforce change control processes. | Adjust scope based on priority, cut non-essential features. | Scope document finalized. | Open
R011 | 15/03/2025 | Difficulty in aligning sponsors, speakers, and partners due to conflicting interests. | Medium | Medium | Medium | Pre-Event | Project Sponsor & Event Strategist | Regular stakeholder meetings, clear communication, and defined expectations. | Re-evaluate partnerships, adjust expectations. | Stakeholder meetings ongoing. | Open
R012 | 15/03/2025 | Misinterpretation of content, language barriers, or cultural sensitivities affecting engagement. | Low | Medium | Medium | Throughout Project | Marketing Team & Event Strategist | Research audience demographics, use multilingual options, and ensure culturally inclusive content. | Provide translations, clarify intent in communication. | Audience research conducted. | Open
Risk Monitoring & Reporting
Risk Review Frequency: Weekly meetings to assess and update risk status.
Reporting Method: Risks will be tracked in a shared document and updated as needed.
Communication Plan: Regular updates to stakeholders via email and team meetings.